## Schedule
PROJECT SCHEDULE
Project Name
Last Updated
Index | Milestones and Tasks / Activities | Start Date | Target Date | Status | Date Completed | Owner | Notes
1
2
3
Using an Index Column
An Index column allows users to sort data in any column and then return to the original order.
After adding or deleting rows, type 1 in the first Index row and 2 in the second Index row. Select both cells and drag the fill handle (lower right corner) to the bottom Index row.
After sorting other columns, sort the Index from smallest to largest to return to the original order.
Drop Down Lists
The Status field uses Data Validation settings to provide a drop down list. Insert or delete rows below to change the drop down options.
Status
Complete
In Progress
Not Started

## Schedule Example
PROJECT SCHEDULE
Project Name
Last Updated
Index | Milestones and Tasks / Activities | Start Date | Target Date | Status | Date Completed | Owner | Notes
1 | Develop Project Charter | 2021-01-04 | 2021-01-15 | Complete | 2021-01-15 | Project Lead
2 | Identify project team members and responsibilities | 2021-01-04 | 2021-01-15 | Complete | 2021-01-15 | Team
3 | Define team logistics (e.g., meeting frequency) | 2021-01-15 | 2021-01-20 | Complete | 2021-01-18 | Team
4 | Sign Project Charter | 2021-01-15 | 2021-01-27 | Complete | 2021-01-29 | Project Lead and Sponsor
5 | Project kick-off meeting | 2021-02-01 | 2021-02-01 | Complete | 2021-02-05 | Project Lead
6 | MILESTONE: Complete project initiation | 2021-01-04 | 2021-02-01 | Complete | 2021-02-05
7 | Develop Project Schedule | 2021-02-05 | 2021-02-20 | In Progress |  | Project Lead
8 | Budget approval | 2021-02-05 | 2021-02-20 | In Progress |  | Sponsor
9 | Establish risk, issue and decision tracking | 2021-02-10 | 2021-02-15 | In Progress |  | Project Lead
10 | Assess change management needs | 2021-02-12 | 2021-02-28 | In Progress |  | Team Members 1 and 2
11 | Develop Communications Plan | 2021-02-15 | 2021-02-28 | Not Started |  | Team Members 2 and 3
12 | MILESTONE: Complete project planning | 2021-02-05
Using an Index Column
An Index column allows users to sort data in any column and then return to the original order.
After adding or deleting rows, type 1 in the first Index row and 2 in the second Index row. Select both cells and drag the fill handle (lower right corner) to the bottom Index row.
After sorting other columns, sort the Index from smallest to largest to return to the original order.
Drop Down Lists
The Status field uses Data Validation settings to provide a drop down list. Insert or delete rows below to change the drop down options.
Status
Complete
In Progress
Not Started